## Sheet1
Id | Feature | Pre-req
F1 | Angularise the calendar
F2 | Refactor the calendar code
F3 | Commit code to GitHub
F4 | Make drop of resource stick to event
F5 | Render the event with added resources | F4
F6 | Allow SPA update of event onClick
F7 | Commit changes to GoogleCalendar when event changes accepted | F6
F8 | Allow for "confirmed", "completed" and "paid" tags to be dragged to events
F9 | Render the event with "confirmed", "completed" and "paid" statuses | F8
F10 | Draw external events from database | F1
F11 | Draw staff from database | F1
F12 | Allow for addition of payment details
F13 | Allow for addition of extra tasks
F14 | Allow for addition of notes
F15 | Render event for additional tasks | F13
F16 | Render event for notes | F14